## Risk Management Matrix
TESLA INVENTORY SYSTEM RISK MANAGEMENT MATRIX
NAME |  |  |  |  | OBJECTIVE
REF/ID | PRE-MITIGATION |  |  |  | MITIGATIONS / WARNINGS / REMEDIES | POST-MITIGATION |  |  |  | RISK SEVERITY KEY | RISK LIKELIHOOD KEY | RISK LEVEL KEY | ACCEPTABLE TO PROCEED? KEY
| RISK | RISK SEVERITY | RISK LIKELIHOOD | RISK LEVEL |  | RISK SEVERITY | RISK LIKELIHOOD | RISK LEVEL | ACCEPTABLE TO PROCEED?
1 | Nobody wants the product | UNDESIRABLE | POSSIBLE | MEDIUM | Need to think carefully about the business case of the project with BOSCARD | ACCEPTABLE | IMPROBABLE | LOW | YES | ACCEPTABLE | IMPROBABLE | LOW | YES
2 | Losing the database | UNDESIRABLE | POSSIBLE | MEDIUM | Will periodically back up the database on Gdrive and Git. | INTOLERABLE | IMPROBABLE | MEDIUM | YES | TOLERABLE | POSSIBLE | MEDIUM | NO
3 | Security flaws with sensitive information (usernames and passwords) | UNDESIRABLE | PROBABLE | HIGH | Unlikely to happen during development as the application will be hosted locally. However, after development has finished, this could be considered by the security team. | UNDESIRABLE | IMPROBABLE | MEDIUM | YES | UNDESIRABLE | PROBABLE | HIGH
4 | Pandemic stops project | UNDESIRABLE | IMPROBABLE | LOW | Will work remotely and pass on the project if there are any issues. | UNDESIRABLE | IMPROBABLE | MEDIUM | YES | INTOLERABLE |  | EXTREME
5 | Loss of data from bad command (i.e. rm -rf * or DROP table) | INTOLERABLE | PROBABLE | EXTREME | Will edit the bashrc file and user privileges on SQL to avoid this from occuring | INTOLERABLE | IMPROBABLE | MEDIUM | YES
6 | Not finishing project on time
CLICK HERE TO CREATE IN SMARTSHEET

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.